## Lofthus
Lofthus |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Thuesday
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
| 1. Research (planning) | 7
| 1.1 Target audience | 2 | bar: Week 1 1 to Week 1 2
| 1.2 Content | 2 | bar: Week 1 3 to Week 1 4
| 1.2 Image search and edit | 2 | bar: Week 1 5 to Week 2 6
| 1.3 Structure | 1 | bar: Week 2 7
| 2. Visual identity (concept) | 8
| 2.1 Logo | 3 | bar: Week 2 8 to Week 2 10
| 2.1 Typography | 2 | bar: Week 3 11 to Week 3 12
| 2.1 Colors | 1 | bar: Week 3 13
| 2.1 Style (shape/elements) | 1 | bar: Week 3 14
| 2.1 Export | 1 | bar: Week 3 15
| 3. Layout | 4
| 3.1 Wireframe sketches | 2 | bar: Week 4 16 to Week 4 17
| 3.2 Mockup | 2 | bar: Week 4 18 to Week 4 19
| 4. Code | 8
| 4.1 HTML | 2 | bar: Week 4 20 to Week 5 22
| 4.2 CSS | 6 | bar: Week 5 23 to Week 6 28
| 5. Testing | 6
| 5.1 Validator HTML/CSS | 2 | bar: Week 6 29 to Week 6 30
| 5.2 Cross testing | 1 | bar: Week 7 31
| 5.3 Error correction | 3 | bar: Week 7 32 to Week 7 34
| 6. Report | 6
| 6.1 Gather files | 1 | bar: Week 7 35
| 6.2 Write report | 4 | bar: Week 8 36 to Week 8 39
| 6.3 Proofread, deliver | 1 | bar: Week 8 40
| 7. Review | 2
| 7.1 Review project | 2 | bar: Thuesday 41 to Thuesday 42
Workdays

## Original
ORIGINAL PLAN
Re-cycle |  |  | Monday |  |  |  |  | Thuesday |  |  |  |  | Wednesday |  |  |  |  | Thursday |  |  |  |  | Friday |  |  |  |  | Saturday |  |  |  |  | Sunday |  |  |  |  | Monday |  |  |  |  | Thuesday
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
| 1. Research (planning) | 7
| 1.1 Target audience | 2 | bar: Monday 1 to Monday 2
| 1.2 Content | 2 | bar: Monday 3 to Monday 4
| 1.2 Image search and edit | 2 | bar: Monday 5 to Thuesday 6
| 1.3 Structure | 1 | bar: Thuesday 7
| 2. Visual identity (concept) | 8
| 2.1 Logo | 3 | bar: Thuesday 8 to Thuesday 10
| 2.1 Typography | 2 | bar: Wednesday 11 to Wednesday 12
| 2.1 Colors | 1 | bar: Wednesday 13
| 2.1 Style (shape/elements) | 1 | bar: Wednesday 14
| 2.1 Export | 1 | bar: Wednesday 15
| 3. Layout | 4
| 3.1 Wireframe sketches | 2 | bar: Thursday 16 to Thursday 17
| 3.2 Mockup | 2 | bar: Thursday 18 to Thursday 19
| 4. Code | 8
| 4.1 HTML | 2 | bar: Thursday 20 to Friday 22
| 4.2 CSS | 6 | bar: Friday 23 to Saturday 28
| 5. Testing | 6
| 5.1 Validator HTML/CSS | 2 | bar: Saturday 29 to Saturday 30
| 5.2 Cross testing | 1 | bar: Sunday 31
| 5.3 Error correction | 3 | bar: Sunday 32 to Sunday 34
| 6. Report | 6
| 6.1 Gather files | 1 | bar: Sunday 35
| 6.2 Write report | 4 | bar: Monday 36 to Monday 39
| 6.3 Proofread, deliver | 1 | bar: Monday 40
| 7. Review | 2
| 7.1 Review project | 2 | bar: Thuesday 41 to Thuesday 42
Workdays

## Reviewed
[10 empty] | Planned time |  |  |  |  | Overdue time |  |  |  |  | Obtained time |  |  |  |  | Not available |  |  |  | Deadline
Re-cycle | Planned | Actual | Monday |  |  | Thuesday | [6 empty] | Wednesday |  |  |  |  | Thursday | [6 empty] | Friday | [5 empty] | Saturday |  |  |  | Sunday | [6 empty] | Monday |  |  | Thuesday
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
1. Research (planning) | 7 | 9 | Thuesday 9: 100%
1.1 Target audience | 2 | 2 | bar: Monday 1 to Monday 2
1.2 Content | 2 | 3 | bar: Monday 3 to Thuesday 5
1.2 Image search and edit | 2 | 3 | bar: Thuesday 6 to Thuesday 8
1.3 Structure | 1 | 1 | bar: Thuesday 9
2. Visual identity (concept) | 8 | 12 | Thursday 22: 100%
2.1 Logo | 3 | 5 | bar: Thuesday 10 to Wednesday 14
2.1 Typography | 2 | 2 | bar: Wednesday 14 to Wednesday 15
2.1 Colors | 1 | 2 | bar: Thursday 16 to Thursday 17
2.1 Style (shape/elements) | 1 | 2 | bar: Thursday 18 to Thursday 19
2.1 Export | 1 | 1 | bar: Thursday 20 to Thursday 22
3. Layout | 4 | 3 | Friday 25: 100%
3.1 Wireframe sketches | 2 | 2 | bar: Friday 23 to Friday 24
3.2 Mockup | 2 | 1 | bar: Friday 25 to Friday 26
4. Code | 8 | 10 | Sunday 35: 100%
4.1 HTML | 2 | 2 | bar: Friday 26 to Friday 28
4.2 CSS | 6 | 8 | bar: Saturday 29 to Sunday 35
5. Testing | 6 | 4 | Sunday 39: 100%
5.1 Validator HTML/CSS | 2 | 1 | bar: Sunday 36 to Sunday 37
5.2 Cross testing | 1 | 1 | bar: Sunday 37
5.3 Error correction | 3 | 2 | bar: Sunday 38 to Monday 41
6. Report | 6 | 3 | Monday 42: 50%
6.1 Gather files | 1 | 1 | bar: Monday 40
6.2 Write report | 4 | 2 | bar: Monday 41 to Monday 42
6.3 Proofread | 1 | 0 | bar: Monday 42
7. Review | 2 | 2 | Thuesday 44: 100%
7.1 Review project | 2 | 2 | bar: Thuesday 43 to Thuesday 44
Workdays | bar: Monday 40 to Monday 42
Child sick days | bar: Thuesday 4 to Thursday 22

## Tasks
| Total 12 | Start from 0 | Total hours 45
| Task | Start date/Time | Hours to complete
Style | Research target audience |  | 2
| Content |  | 2
| Visual identity |  | 10
| Image search |  | 2
Code | Planning |  | 5
| Code research |  | 2
| HTML document |  | 2
| CSS document |  | 6
Testing | Validator (HTML CSS) |  | 2
| Cross testing |  | 1
| Report |  | 5
39
1. The Gantt chart should now give you a good overview on how much time you have spent on different activities. Have you been effective and used less than 40 hours? Did you use more than 40 hours? Which activities took the most time? Could you plan your time differently the next time?
Effective vs. slow
New plan (eliminate)